## Sheet1
Risk ID | Asset / Process | Threat | Vulnerability | Existing Controls | Likelihood (1–5) | Impact (1–5) | Inherent Risk Score | Risk Level | Risk Owner | Risk Treatment | Treatment Actions | Target Controls | Residual Likelihood | Residual Impact | Residual Risk Score | Residual Risk Level | Status | Linked Incident ID | Evidence File
R-011 | HR Payroll System | Unauthorized access | Weak password policy; no MFA | Password policy; audit logs | 3 | 4 | 12 | Medium | IT Security Manager | Mitigate | Enforce MFA; review access | A.9.2, A.9.4, A.12.4 | 3 | 4 | 12 | Medium | Open | IR-2024-000 | incident-placeholder.md
R-012 | Corporate Email System | Phishing attack | Insufficient user awareness; no MFA | Basic spam filtering; password policy | 4 | 4 | 16 | High | IT Security Manager | Mitigate | Implement MFA; phishing training | A.6.3, A.8.23, A.5.17 | 2 | 3 | 6 | Low | Open | IR-2024-001 | incident-report.md